ARKOVA

DocuSign Integration

Sprint 3 Planning Document

Prepared 2026-05-28  |  SOC 2 Type II Compliant

Sprint Window: 2026-05-28 through 2026-06-11

Team: 2 SR Full-Stack  |  1 SR Frontend/Designer  |  1 SR QA

Epics: SCRUM-1048 (Connectors V2)  |  SCRUM-1866 (Attestation Chain)  |  SCRUM-858 (GME10)

# Table of Contents

# 1. Executive Summary

Sprint 3 of the DocuSign integration (2026-05-28 through 2026-06-11) focuses on landing soaking PRs, shipping security-critical Go-Live prerequisites (Zod validation, rate limiting, DLQ), and starting the legally binding attestation chain.

The team consists of 2 SR Full-Stack developers, 1 SR Frontend/Designer, and 1 SR QA engineer. All work follows SOC 2 Type II standards including TDD, staging soaks, and mandatory audit trails.

Current State Summary:

- Sprint 2 code-complete (PR #924 and #927 soaking)

- 6 stories Done, 9 In Progress, 19 To Do

- 3 new gap stories created this session (SCRUM-2132, 2133, 2134)

- PR #867 (action modes) blocked on staging — being worked separately

# 2. Current State

## 2.1 What’s Shipped (Done)

| Story | Summary | PR |
| --- | --- | --- |
| SCRUM-1101 | DocuSign Connect webhook (HMAC-verified) | #509, #812 |
| SCRUM-1168 | Integration OAuth + KMS token storage | merged |
| SCRUM-1648 | Org-wide capture (multi-sender + auth + dedupe) | #689 |
| SCRUM-1864 | BUG: OAuth token KMS config fallback | #840 |
| SCRUM-862 | E-signature audit-trail parsing | #515 |
| SCRUM-863 | Pre/post-signing anchor workflow | #515 |

## 2.2 What’s Soaking (Hands-Off)

| Stories | PR | Tier | Soak Ends |
| --- | --- | --- | --- |
| 2039 (audit) + 2040 (Sentry) + 2041 (health) | #924 | T2 | ~05-28T04:00Z |
| 2042 (reconciliation) + 2043 (HMAC) + 2044 (member) | #927 | T2 | ~05-28T05:00Z |

## 2.3 What’s Blocked

| Story | PR | Issue |
| --- | --- | --- |
| SCRUM-1649 (action modes) | #867 | T3 soak blocked — staging dirty. Worked elsewhere. |

## 2.4 In Progress (No PR)

| Story | Summary |
| --- | --- |
| SCRUM-1871 | legally_binding_attestations table + state machine |
| SCRUM-1624 | Post-signing anchor endpoint (GME10) |

# 3. Gap Analysis

## 3.1 Research-Driven Corrections

| # | Gap | Action |
| --- | --- | --- |
| G1 | SCRUM-2070 said 1000 req/hr — actual is 3,000/hr | FIXED: Ticket updated |
| G2 | No JWT Grant migration story for worker | CREATED: SCRUM-2132 |
| G3 | No dynamic base URI resolution for prod | Verify in codebase; fold into 2069 |
| G4 | No Connect listener reprovisioning subtask | Add subtask to SCRUM-2069 |
| G5 | No vendor risk assessment (CC9.1/CC9.2) | CREATED: SCRUM-2134 |
| G6 | SCRUM-2099 overlaps with SCRUM-2042 | Clarified: complementary, not dupl. |
| G7 | No E2E test story for DocuSign UI | CREATED: SCRUM-2133 |
| G8 | SCRUM-1293 has no subtasks | FIXED: 3 subtasks created |
| G9 | Attestation chain deep sequential dep | Plan SCRUM-1626 into sprint |

## 3.2 Jira Structure Audit

All 26 DocuSign stories have correct parent epics. All stories have subtasks (SCRUM-1293 was the only gap — fixed). All 7 PR-associated stories correctly show In Progress.

# 4. DocuSign Best Practices Research

## 4.1 Connect Webhook

- Retry: 45 retries over 7 days. First 3 within ~1 minute, then exponential backoff up to 8hr

- Acknowledgment: 100 seconds to return HTTP 200. Accept immediately, queue async.

- HMAC: Up to 2 concurrent keys. SHA-256 over raw body. Zero-downtime rotation.

- Replay: No timestamp header from DocuSign. Must implement via connectCorrelationId dedup.

## 4.2 API Rate Limits

3,000 requests/hour/account (not 1,000). Burst: ~500/30s. Polling listStatusChanges: max once per 15 min. On 429: respect Retry-After, exponential backoff with jitter.

## 4.3 OAuth Token Lifecycle

JWT Grant (recommended for worker): 1hr access token, no refresh token. Re-request via JWT assertion.

Auth Code Grant with extended scope (for member OAuth): 30-day sliding refresh. Proactive refresh cron every 25 days.

## 4.4 Go-Live Cutover

Automated review (~20 min). Must reprovision: Connect listeners, HMAC keys, OAuth consent on production. Base URLs change to dynamically-resolved URIs via /oauth/userinfo.

## 4.5 WORM Retention

GCP Cloud Storage with retention policy + bucket lock = WORM-compliant. Store raw payloads, signed PDFs, Certificates of Completion. SHA-256 hashes. 7-year retention for legal docs.

# 5. Dependency Map

Already Soaking (hands-off):

PR #924 (SCRUM-2039/2040/2041) and PR #927 (SCRUM-2042/2043/2044) — merge when soak passes.

Blocked:

PR #867 (SCRUM-1649 action modes) — needs clean staging, then 48h T3 soak.

Attestation Chain:

SCRUM-1871 (table) → SCRUM-1872 (notary webhook). SCRUM-1626 also blocks 1872. Then 1872 → 1873 (endpoint) → 1874 (UI).

Go-Live Prerequisites (must ship before SCRUM-2069):

SCRUM-2072 (Zod) + 2070 (rate limits) + 2095 (DLQ) + 2097 (WORM) + 1649 (action modes).

# 6. Complete Work Inventory (28 Stories)

## 6.1 SCRUM-1048 (CONNECTORS-V2) — 21 Stories

| Pri | Story | Summary | Status | Tier | SP |
| --- | --- | --- | --- | --- | --- |
| P0 | SCRUM-1649 | Action modes (instant-secure + queue) | Blocked | T3 | 8 |
| P0 | SCRUM-2072 | Webhook payload Zod validation | To Do | T2 | 3 |
| P0 | SCRUM-2070 | API rate limit (3,000/hr) | To Do | T2 | 5 |
| P0 | SCRUM-2095 | Document-fetch DLQ + requeue | To Do | T2 | 5 |
| P1 | SCRUM-2097 | WORM retention (365d) | To Do | T2 | 5 |
| P1 | SCRUM-2098 | Listener drift reconciliation | To Do | T2 | 3 |
| P1 | SCRUM-2099 | Failures API poller | To Do | T2 | 3 |
| P1 | SCRUM-2071 | DR runbook | To Do | T1 | 3 |
| P1 | SCRUM-2100 | IDV tier capture | To Do | T2 | 5 |
| P1 | SCRUM-2101 | Member offboarding | To Do | T2 | 5 |
| P1 | SCRUM-2132 | JWT Grant migration (NEW) | To Do | T2 | 5 |
| P1 | SCRUM-2133 | UI E2E tests (NEW) | To Do | T1 | 3 |
| P1 | SCRUM-2134 | Vendor risk assessment (NEW) | To Do | T1 | 2 |
| P2 | SCRUM-2045 | Sub-org isolation | To Do | T2 | 8 |
| P2 | SCRUM-2094 | Volume test harness | To Do | T1 | 5 |
| P2 | SCRUM-2096 | Health admin dashboard | To Do | T1 | 8 |
| P3 | SCRUM-2069 | Sandbox-to-prod cutover | To Do | T3 | 8 |
| P3 | SCRUM-1293 | Webhook idempotency | To Do | T2 | 5 |

## 6.2 SCRUM-1866 (Attestation Chain) — 4 Stories

| Pri | Story | Summary | Status | Tier | SP |
| --- | --- | --- | --- | --- | --- |
| P1 | SCRUM-1871 | Attestation table + state machine + RLS | In Prog | T2 | 5 |
| P1 | SCRUM-1872 | Notary webhook handler | To Do | T2 | 5 |
| P2 | SCRUM-1873 | Attestation initiation endpoint | To Do | T2 | 5 |
| P2 | SCRUM-1874 | Attestation UI + public verification | To Do | T1 | 8 |

## 6.3 SCRUM-858 (GME10) — 3 Stories

| Pri | Story | Summary | Status | Tier | SP |
| --- | --- | --- | --- | --- | --- |
| P1 | SCRUM-1624 | Post-signing anchor endpoint | In Prog | T2 | 5 |
| P1 | SCRUM-1626 | Signing-complete webhook (blocks 1872) | To Do | T2 | 5 |
| P2 | SCRUM-1625 | Proof Package ZIP generator | To Do | T2 | 5 |

# 7. Sprint 3 Plan (2026-05-28 to 2026-06-11)

## 7.1 Sprint Goal

Land the soaking PRs, ship Zod validation + rate limiting + DLQ (security-critical Go-Live prerequisites), and start the attestation chain.

## 7.2 Team Capacity

| Role | Person-Days | Effective (70%) |
| --- | --- | --- |
| 2 SR Full-Stack | 20 | 14 |
| 1 SR Frontend/Designer | 10 | 7 |
| 1 SR QA | 10 | 7 |
| Total | 40 | 28 |

## 7.3 Week 1: Land Soaking PRs + Security-Critical

| # | Story | Assignee | Days | Notes |
| --- | --- | --- | --- | --- |
| 1 | Merge PR #924 | Tech Lead | 0.5 | Soak completes 05-28. Verify + merge. |
| 2 | Merge PR #927 | Tech Lead | 0.5 | Soak completes 05-28. Verify + merge. |
| 3 | SCRUM-2072 Zod | Full-Stack A | 3 | Zod schemas for all webhook payloads. TDD. |
| 4 | SCRUM-2070 Rate limit | Full-Stack B | 3 | 3,000/hr guardrail, backoff, 429 handling. |
| 5 | SCRUM-1871 Attestation | Full-Stack B | 3 | Migration + state machine + RLS + TLA+. |
| 6 | SCRUM-2071 DR runbook | QA | 3 | Recovery procedures + vendor risk (CC9). |
| 7 | SCRUM-2133 UI E2E | Frontend | 3 | Playwright: connect/disconnect/settings. |

## 7.4 Week 2: DLQ + WORM + Attestation Unblock

| # | Story | Assignee | Days | Notes |
| --- | --- | --- | --- | --- |
| 8 | SCRUM-2095 DLQ | Full-Stack A | 3 | Dead letter queue for failed doc fetches. |
| 9 | SCRUM-2097 WORM | Full-Stack B | 3 | GCS bucket, retention policy + lock. |
| 10 | SCRUM-1626 Webhook | Full-Stack A | 2 | Unblocks 1872. DocuSign + Adobe. |
| 11 | SCRUM-2096 Dashboard | Frontend | 5 | Integration status, webhook stats, health. |
| 12 | Soak coordination | QA | 4 | T2 soaks, rollback rehearsals, evidence. |

## 7.5 Sprint 3 Metrics

| Metric | Value |
| --- | --- |
| Stories committed | 10-12 (including 3 merges) |
| Story points | ~45 |
| New migrations | 2-3 |
| Soak tiers | 4-5x T2 |
| Go-Live prereqs closed | 3 of 6 (Zod, rate limit, DLQ) |

# 8. Sprint 4+ Roadmap

## Sprint 4: Go-Live Readiness

SCRUM-2069 (cutover), SCRUM-2098 (listener drift), SCRUM-2099 (Failures API), SCRUM-2101 (offboarding), SCRUM-1872 (notary webhook), SCRUM-2132 (JWT Grant), SCRUM-2094 (volume test).

## Sprint 5: Attestation Chain + Sub-orgs

SCRUM-1873 (attestation endpoint), SCRUM-1874 (attestation UI), SCRUM-2045 (sub-org isolation), SCRUM-2100 (IDV tier), SCRUM-1625 (Proof Package ZIP), SCRUM-1293 (webhook idempotency).

# 9. SOC 2 Type II Control Coverage

| CC Control | Area | Stories | Sprint |
| --- | --- | --- | --- |
| CC6.1 | Credential storage | 2043 (dual HMAC) — shipped | S2 |
| CC6.6 | Third-party access | 2132 (JWT) + 2134 (vendor) | S3-S4 |
| CC6.7 | Data transmission | 2072 (Zod) + 2043 (HMAC) | S2-S3 |
| CC7.1 | Monitoring | 2040 (Sentry) — soaking | S2 |
| CC7.2 | Detection | 2039 (audit) + 2042 (reconciliation) | S2 |
| CC7.3 | Incident response | 2071 (DR runbook) | S3 |
| CC7.4 | Remediation | 2095 (DLQ + requeue) | S3 |
| CC8.1 | Change mgmt | 2098 (drift) + 2133 (E2E) | S3-S4 |
| CC9.1-9.2 | Vendor risk | 2134 (vendor assessment) | S3 |
| A1.2 | Recovery | 2071 (DR) + 2099 (Failures) | S3-S4 |

# 10. Jira Changes Made This Session

## New Stories Created

| Key | Summary | Parent | Subtasks |
| --- | --- | --- | --- |
| SCRUM-2132 | Worker JWT Grant migration | SCRUM-1048 | 2135, 2136, 2137 |
| SCRUM-2133 | DocuSign UI E2E tests | SCRUM-1048 | 2138, 2139, 2140 |
| SCRUM-2134 | Vendor risk assessment | SCRUM-1048 | 2141, 2142, 2143 |

## Tickets Updated

| Key | Change |
| --- | --- |
| SCRUM-2070 | Summary corrected: 1,000 req/hr → 3,000 req/hr. Description updated. |
| SCRUM-1293 | 3 subtasks added: SCRUM-2144, 2145, 2146 |

# 11. Immediate Actions

| # | Action | Owner | When |
| --- | --- | --- | --- |
| 1 | Merge PR #924 and #927 when soaks pass | Carson | 2026-05-28 |
| 2 | Sprint 3 kickoff with team | PM | Day 1 |
| 3 | Verify dynamic base URI resolution (Gap G3) | Tech Lead | Day 1 |
| 4 | Add Connect reprovisioning subtask to 2069 | PM | Day 1 |
| 5 | Create Confluence pages for 2132, 2133, 2134 | PM | Day 2 |
| 6 | Begin SCRUM-2072 + SCRUM-2070 | Full-Stack A+B | Day 1 |

Document prepared by PM  |  2026-05-28  |  Arkova DocuSign Integration Sprint 3